## Backlog
Kakehashi combined backlog
Reviewed 2026-09-09. Priority and difficulty are reviewed estimates. Difficulty: 1 easy to 5 very hard. Effort includes focused verification.
|  |  |  | Work items | 51 | Original reports reviewed | 80
|  |  |  | P1: Next | 9 | P2: Soon | 26 | P3: Later | 16
Rank | Work ID | Priority | Difficulty | Work item | Effort | Next action | Current status | Why this priority / remaining scope | Report refs | Related work
1 | B01 | P1 | 3 | Lesson notes disappear after saving | 1–3 days after verification | Check note survives save, lesson completion, route exit, restart and remote refresh; fix persistence or cache overwrite if reproduced. | Reported data loss; resolution unconfirmed | User-authored reading/meaning notes disappear after lessons, damaging trust and losing work. | C33
2 | B02 | P1 | 4 | Keyboard switching, corrupt input and iPad focus | 2–4 days after reproduction | Reproduce SwiftKey character corruption first. Treat auto-switch compatibility and iPad keyboard persistence as separate remaining slices. | Corrupt input reported; related keyboard gaps | Incorrect text while typing/deleting can cause wrong grading. Existing auto-switch settings do not resolve reported third-party keyboard failures. | C44
3 | B03 | P1 | 4 | Slow startup and completion on poor connections | 2–4 days | Bound startup/update and completion waits; let reviews finish locally and synchronize queued progress later. | Reported; connection trigger needs reproduction | Minutes-long startup and completion stalls obstruct the core study loop. Developer acknowledges work needed but assumes weak connectivity; existing offline storage does not establish that waiting behavior is fixed. | C01 | B04, B09
4 | B04 | P1 | 4 | Lessons and reviews unavailable fully offline | 2–4 days | Reproduce fully offline lessons/reviews with a previously synchronized account; fix cache/bootstrap readiness and offline entry. | Unresolved; no fix confirmation. | Complete loss of the core study workflow offline, beyond the separate slow-network timeout report. | C30 | B03
5 | B05 | P1 | 4 | Android vocabulary lessons stall and audio overlaps | 0.5–1 day profiling; 3–5 days if present | Profile current Android lesson loading and audio taps; fix remaining main-thread stall, coalescing repeated playback requests. | Reported; partial mitigations exist | Multiple Android users unable to study vocabulary for 10–60 seconds with overlapping audio. Current source has deferred state updates, loading UI and audio request identity checks, so do not assume historical bug persists or that mitigations prove fixed. | C55
6 | B06 | P1 | 3 | Android review kanji shrink to unreadable size | 1–2 days | Merge with C39 and reproduce Android prompt autosizing across Gboard show/hide and question changes. | Recurrence after earlier attempted fix | Makes core question text unreadable; multiple devices/users and temporary exit/reenter workaround. | C38, C39, C62
7 | B07 | P1 | 3 | Android review text clipped | 1–2 days | Reproduce clipped review prompts with keyboard, long vocabulary and font settings; correct layout measurement. | Reported; reproduce | Unreadable prompts interfere with core reviews. Clipping is related to, but distinct from, tiny-font reports. | C62, G54
8 | B08 | P1 | 3 | Multiple-choice answers disappear | 1–2 hours QA; 1–2 days if present | Test persisted mode, repeated questions and audio quiz on Android; fix empty choice panels if the issue remains. | Verify recent changes | Recent changes in #64 address eligibility and remove the older toggle; the reported blank menu is not proven resolved. | G72 | B10
9 | B09 | P1 | 3 | Dashboard lesson and review counts become stale | 2–4 days | Consolidate stale dashboard counts with C24; reproduce refresh-overwrite and reconcile caches. | Multiple corroborating reports | Multiple users saw lessons/reviews far above actual and refresh briefly showed correct count then reverted. Core progress trust issue; learned-kanji definition explains only some count differences. Same main outcome as C24. | C24, C53 | B03, B18
10 | B10 | P2 | 3 | Multiple-choice back-to-back behaviour | 1–2 days; narrow reproduction first | Verify radical choices after fix; reproduce back-to-back reading/meaning with reporter settings, then fix or close the remaining interaction. | Feature delivered; latest back-to-back problem remains unconfirmed | Developer and reporter confirm multiple choice mostly works, including follow-up fixes; final developer comment says back-to-back failure could not be reproduced. Do not estimate a new multiple-choice implementation. | C03 | B08
11 | B11 | P2 | 3 | Reliable links in subject notes | 1–2 days | Finish remembered character suffix and link toggling; verify selection, cursor, Japanese input and clipboard behaviour. | Local draft changes | Earlier link fixes merged in #78; last requests have uncommitted implementations and need verification. | C09, C14, G65 | B01, B12
12 | B12 | P2 | 3 | Note editor usability and formatting extensions | 0.5–1 day QA; 2–4 days extensions | Verify merged small-iPhone layout/keyboard fixes; preserve configurable highlights, strikethrough and rich clipboard requirements. | Partial implementation | Bold/italic/underline and visual editing already exist. #78 addresses layout; remaining formatting additions are P3, while usability verification is P2. | C14, G68 | B11, V03
13 | B13 | P2 | 3 | Review word obstruction | 1–2 days; current-device reproduction first | Verify long review words with previous-answer card visible before reveal; reserve layout space and prevent scroll gestures revealing answers if still reproducible. | Unresolved old iPhone report; later typography fixes may affect reproduction | Prompt obstruction harms answering; reporter says scrolling works only after reveal and may accidentally reveal. Needs current reproduction, not assumed fixed by generic font work. | C21
14 | B14 | P2 | 2 | Vocab reviews not centered; level & SRS not visible | 1–2 days | Show level/SRS metadata alongside visible context hints and adjust prompt alignment with external keyboards. | Current code still suppresses metadata in this combination. | Two reports demonstrate incompatible enabled settings; localized review layout problem. | C37
15 | B15 | P2 | 2 | iPhone lesson notes and reading hints are clipped | 1–2 days | Reproduce long notes and reading hints in unified lessons; fix clipped content and glyphs on affected iPhones. | Related reports; current-device check needed | Reporter clarified actual truncation rather than inability to scroll. Recent editor/render changes mean first verify; no direct closure confirmation. | C16, C46, C58 | B31
16 | B16 | P2 | 3 | Large-text kanji and radical layouts | 2–3 days | Fix kanji/radical overflow at larger text sizes. Scaling controls already exist; Mac audio is tracked under C32. | Partially implemented; author explicitly says added scaling is unusable in kanji/radical layouts. | Accessibility enhancement exists but breaks reading of key content at high scale. | C40 | B33
17 | B17 | P2 | 3 | [Android] Daily Lesson Reminder issues | 1–3 days after reproduction | Verify duplicate cancellation; if still reproducible, serialize daily reminder scheduling and reconcile external study when refreshed. | Old bug, partial defensive code exists | 27 duplicate notifications is significant reliability friction. Current cancellation scans all scheduled lesson-reminder IDs; concurrent rescheduling and external WaniKani completion still require device validation. Distinct from C02 review-notification grouping. | C52
18 | B18 | P2 | 3 | review forecast duplicate | 1–2 days | Reproduce warm-cache startup and reconcile Now/current-hour counts from one consistent assignment snapshot. | Unresolved stale-data display bug | Temporary duplicate counts self-correct after sync but misrepresent workload. Distinct from generic wrong count reports unless shared trigger established. | C19
19 | B19 | P2 | 3 | Music lyrics not working? | 1–3 days investigation/fix; provider failure may require fallback work | Reproduce automatic and manual lyrics search on Android; separate transport/provider failures from no-results. Track Spotify connection separately unless same cause is proven. | Unresolved corroborated Android issue | Developer suspected temporary service outage, but later two users report all songs/manual searches failing across Android devices. Cannot close from earlier works-for-me reply. | C18
20 | B20 | P2 | 4 | AirPlay and screen share don’t work | 2–4 days with reproducible AirPlay/device setup | Reproduce AirPlay geometry/keyboard occlusion; fix layout state recovery across session changes. | Attempted fix; later report still broken | Initial kanji disappearance changed to keyboard hiding answer input after attempted fix. Reporter provides workaround activating keyboard in another screen first. Distinct external-display trigger; do not assume same cause as Android layout. | C64
21 | B21 | P2 | 3 | Android delayed back navigation and image uploads | 1–3 days | Prevent delayed repeated Back taps from exiting a review; reproduce sub-limit screenshot upload failures. Text defects are tracked separately. | Unresolved navigation and upload reports | The clipping and tiny-font complaints are consolidated under G54 and C38. This work item preserves the distinct double-navigation and attachment failures. | C62 | B06, B07
22 | B22 | P2 | 2 | Submit context multiple-choice answers in one tap | 0.5–1 day | Submit the tapped choice directly and preserve pause/next-question behaviour and duplicate-submit protection. | Ready to implement | Small repeated-flow improvement; current choice press only selects an index before a separate submit. | G76
23 | B23 | P2 | 2 | Play context sentence audio after correct answers | 0.5–1.5 days | Add after-correct playback timing and replay access without racing automatic question advancement. | Existing audio foundation | Speech, speed and replay controls exist; present autoplay runs at question start and feedback stops it. | G75
24 | B24 | P2 | 4 | Undo last answer | 3–5 days | Design reversible recent-answer handling with deferred submission, then implement Anki undo and correct-answer reversal. | Unresolved; repeated follow-ups through 2026-09-03. | Protects study accuracy after accidental ratings. Requires preserving session/SRS state and respecting already-submitted WaniKani results; not a simple back button. | C29
25 | B25 | P2 | 3 | Export context sentences to AnkiDroid | 2–4 days | Refresh the existing Android export branch, verify permission/deck/field setup, and test text export on device. | Unmerged implementation | Implementation exists on f/anki-export-android. Estimate is remaining text-export integration, excluding audio/images and iOS. | G58
26 | B26 | P2 | 2 | Transfer lists and subjects | 1–2 days | Add separate row selection and select-all/move/copy/remove actions inside the List tab; reuse transfer logic. | Earlier whole-list transfer exists; requested bulk-selection UI remains | This extends C20: asks to choose a subset in the current List tab rather than transfer the current membership set. Existing per-list transfer passes all selectedSubjectIds. | C12, C27
27 | B27 | P2 | 2 | Custom subject list filter | 1–2 days for remaining slices | Close confirmed original sorting/dismiss/scroll fixes; separately verify small-screen filter modal and add list sorting to lesson/review pickers. | Original requests confirmed fixed; later requests unresolved | Requester confirms original three fixes on June 9, then asks picker parity; another user reports iPhone SE filter clipping. Current custom-list sorting and scroll restoration exist. | C49
28 | B28 | P2 | 2 | Recent Unlocks Suggestion | 1–2 days | Preserve delivered started-state indication/filter; add select-unstarted → lesson queue action. | Partly implemented; requested lesson launch absent | Developer explicitly says starting lessons from unlock page still absent, and current page filters not-started items but shows no lesson queue/start action. Reuse existing lesson picker/session paths. | C59
29 | B29 | P2 | 3 | Combine iOS Notifications | 1–3 days; native release required | Replace earlier delivered review notifications when a newer one arrives; verify overnight/background behavior in an iOS build. | Accepted; not confirmed delivered | Hourly notifications accumulate and annoy users. Native scheduling/replacement behavior and background execution require more than changing display grouping. | C02
30 | B30 | P2 | 3 | Stroke order visualization | 1–2 days | Reproduce stroke-order animation on affected iPhone/iPad with accessibility and reduced-motion settings; inspect animation lifecycle. | Unresolved; two distinct Apple-device reports, no confirmed fix. | Breaks a study aid but ordinary reviews remain possible. More evidence is needed to distinguish never-starting from prematurely-completing animation. | C45
31 | B31 | P2 | 2 | Select and copy lesson text | 0.5–1.5 days | Verify and restore selectable meaning/reading/example text where requested. Hint clipping is grouped under C16; the initial batch-size issue self-resolved. | Selection scope remains; batch size resolved | User confirms two-lesson batching works after first batch. Unified lesson hint clipping matches C16/C58; current sentence/translation Text is selectable, but full selectable coverage needs checking. | C46 | B15
32 | B32 | P2 | 3 | Small reset bug | 1–2 days | Reproduce duplicated reset-history bars and correct event/history deduplication or classification. | Unresolved; explanation disputed by reporter | Developer initially explained gray current-level bar; reporter clarified two dark reset bars besides current level. Need actual progression/reset fixture; current reset-aware utilities alone do not prove graph fixed. | C61
33 | B33 | P2 | 3 | Mac context audio and vacation statistics follow-up | 1–3 days for audio; statistics unestimated | Verify Mac context speech. Separately identify the vacation-history/statistics symptom from the supplied example before estimating that follow-up. | Audio support unclear; statistics needs detail | Original Mac-audio question and a separate vacation-statistics complaint share one report. Neither should be silently discarded or treated as one root cause. | C32, C40 | B16
34 | B34 | P2 | 4 | Save sentences from multiple sources to review lists | 4–8 days for capture/list/manual review MVP; SRS separate | Implement reusable sentence capture and list storage across sources, then review selected sentences; scope scheduling separately. | Accepted; notebook and custom-SRS foundations exist, universal native sentence lists not established | Four likes and multiple corroborating comments; recurrent workflow spanning WaniKani, custom sentences, anime/news/music. Saving a sentence is a different outcome from exporting it to Anki. | C04 | B25, B35, B45
35 | B35 | P2 | 4 | Integrated notebook and shared sentences | 1–2 weeks | Bridge native subject cards/context practice to shared notebook sentences and prepare rollout. Track handwriting separately. | Partial; restricted rollout | Notebook foundation and web bidirectional sentence editing merged in #73; native integration and public rollout remain. The later handwriting request is a P3 extension with substantial local drafts, requiring separate device validation and completion estimate. | C08, G66 | B34, B45
36 | B36 | P3 | 2 | Audio-only vocab reviews | 0.5–1.5 days for answer display; verify existing behavior first | Keep completed audio-only/reading work closed; add the latest requested kanji representation or compact answer-display preference. | Original feature and reading display delivered; kanji/customizable reveal follow-up open | Reporter thanked the developer twice, then specifically asked for kanji on revealed answers. This is a small extension, not a new listening mode. | C05
37 | B37 | P3 | 2 | Temporarily mute audio | 0.5–1.5 days | Add a session-only autoplay override in existing review controls; restore saved preference for the next session. | Unresolved enhancement; placement needs restraint | Avoid toggling persistent settings each session; one commenter objects to extra screen clutter. Use existing settings/overflow space if available. | C17
38 | B38 | P3 | 2 | Avoid fallback-font flicker during reviews | 0.5–1 day | Preload or cache the chosen font and keep it stable through a question; check cold starts and downloaded fonts. | Likely present | Optional fonts hydrate after initial rendering. Cosmetic and separate from tiny or clipped prompt bugs. | G77
39 | B39 | P3 | 2 | Level recap animation overlaps | 0.5–1.5 days | Reproduce overlapping badges, stabilise landing positions and verify phone/tablet layouts. | Reported; reproduce | Visible animation defect outside the core study flow; no targeted fix found. | G50
40 | B40 | P3 | 2 | Anime Title Formatting | 0.5–1 day | Normalize/display canonical anime titles while preserving source identifiers and punctuation. | Unresolved cosmetic request. | Does not affect the learning functionality; external source metadata may require explicit canonical-title mapping. | C31
41 | B41 | P3 | 2 | Vocabulary Kanji Composition | 1–2 days | Expose optional vocabulary kanji composition on Anki answer reveal, reusing cached components. | Unresolved enhancement | Useful answer detail with existing component data; less urgent than correctness/blocked study. Current paused-detail hydration explicitly excludes effectiveAnkiCardMode, so generic detailed-answer support does not settle this request. | C15
42 | B42 | P3 | 2 | Beginner reading aids and remaining romaji option | 1–2 days for remaining romaji display | Finish optional romaji display if desired. On/kun speech, grouped examples and random order were added; bulk list actions remain under C12. | Partially implemented. | User confirms iOS on/kun speech works; reading-grouped examples and random ordering were answered, parts-of-speech filters exist. Romaji display remains unconfirmed. | C27 | B26
43 | B43 | P3 | 3 | Kana frequency and JLPT coverage refinements | 2–4 days for remaining frequency-form and coverage refinements | Retain kana-versus-kanji frequency rank display; verify frequency thresholds and JLPT filters in remaining games. Preserve completed JLPT, frequency and radical features. | Mostly implemented with residual feature requests. | Author explicitly confirms JLPT lists and frequency display. Later code includes frequency-threshold custom reviews, crossword JLPT filters, and inline radical reminders. Separate kana-versus-kanji frequency display still appears absent. | C22, C28 | V19
44 | B44 | P3 | 3 | Additional level stats | 2–3 days | Define and add projected WaniKani completion date; retain separate haptics support follow-up if still reproducible. | Feature outstanding; developer says it never existed. | A useful planning statistic, lower impact than study reliability. Haptics comment has settings guidance, not a confirmed defect. | C25
45 | B45 | P3 | 5 | Custom context sentence improvements | Several weeks; small slice 1–2 days | Separate custom-first order and speech speed from saved sentence selection, kana/furigana, bilingual alignment and constrained AI generation. | Split mixed scope | Six requests including the comment. Small ordering/audio improvements merit P2; alignment and AI vocabulary restrictions need separate scoping. | G71 | B34, B46
46 | B46 | P3 | 5 | Japanese-to-Japanese learning options | Several weeks or more | Start with hidden-English gaps and audio-to-Japanese modes; scope Japanese answer policy, dictionary, picture quizzes and localisation separately. | Split product scope | Full request spans seven features. Existing hidden-translation and audio foundations help, but dictionary/content and localisation remain major work. | G80 | B36, B45
47 | B47 | P3 | 4 | Interleave lessons and reviews (suggestion) | 4–7 days | Define mixed-session scheduling and introduce a controlled lesson/review interleaving option. | Unimplemented enhancement; no comments. | Changes the central session model and progress semantics for an optional workflow. | C34
48 | B48 | P3 | 3 | Context Sentence TTS Voice | 1–3 days feasibility/prototype, implementation depends on available voices | Investigate native Japanese voice selection only if still needed with current cloud TTS; communicate supported voice choices. | Siri voice request unresolved; enhanced-voice workaround confirmed | Unlike broad C51 quality feedback, this explicitly requests selecting Siri Japanese voices. Current native fallback passes language/rate without a voice identifier; cloud voice restoration does not fulfill native Siri selection. | C57
49 | B49 | P3 | 4 | Apple Watch review-count complication | 3–5 days | Add a review-count complication to the Watch companion. Lockscreen widget is delivered; repeated handwriting loading is tracked under C65. | Complication outstanding; lockscreen delivered | Requester confirmed lockscreen widget May 19 and supplied a precise repeated-session freehand repro May 31. Watch scaffold/audit explicitly lacks complication support; full Watch reviews C67 is separate scope. | C56, C67 | B50, V04
50 | B50 | P3 | 5 | Apple Watch reviews | 1–3 weeks remaining | Continue existing Watch branch only after core reliability fixes; reconcile submission/session/cache hazards and validate paired release. | Substantial unmerged branch; release checks remain | Current refined Watch branch integrated main and physical installs were attempted; documented blockers remain around stale replies, double count, phone cache/recovery, radicals and logout. No real review submissions verified. C56 complication is a separate smaller feature, not satisfied by review app. | C67 | B49
51 | B51 | P3 | 5 | Adding a cbz/cbr manga reader | 2–4 weeks for public-quality OCR and requested format coverage | Treat as unreleased prototype: decide whether basic reading can ship separately from OCR quality, and specify CBR support. | Existing hidden reader prototype; not fulfilled publicly. | Developer says on-device OCR fails roughly half the time; code accepts CBZ/images but does not show CBR support. Consider product scope before committing. | C43

## Verify and close
Verify, clarify and close
Reviewed 2026-09-09. Priority and difficulty are reviewed estimates. Difficulty: 1 easy to 5 very hard. Effort includes focused verification.
|  |  |  | Work items | 23 | Original reports reviewed | 80
|  |  |  | Verify | 14 | Close / Archive | 8 | Clarify | 1
Rank | Work ID | Priority | Difficulty | Work item | Effort | Next action | Current status | Why this priority / remaining scope | Report refs | Related work
1 | V01 | Verify | 1 | Resume only the originally selected lessons | 0.5–1 hour | Smoke-test an Android build containing #79, then close if the selected remaining lessons resume correctly. | Merged fix; verify release | Merged fix uses stable assignment IDs and preserves picked sessions; regression tests cover reordering/removal. | G70
2 | V02 | Verify | 1 | External keyboard answers lose final characters | 1–2 hours | Verify rapid typing and Enter on an external keyboard in a build containing PR #64; reopen implementation only if characters still disappear. | Likely fixed in #64; hardware check needed | False wrong answers are serious, but current code specifically captures native submission text and resets before new input. | C35
3 | V03 | Verify | 2 | Android lesson-note keyboard repeatedly opens/closes | 1–2 hours; 1–2 days if persistent | Verify Android lesson note keyboard remains stable on Pixel with current plain/rich editor; keep separate from note durability. | Verify recent editor fixes on Pixel | Keyboard opening/closing rapidly prevents note entry. Recent code targets this area but no report confirmation. | C41
4 | V04 | Verify | 3 | Repeated handwriting sessions get stuck loading | ½–1 day repeated-session verification; 1–3 days fix if reproduced | Verify exact repeat-session freehand repro using C56 comments; close confirmed redraw/layout requests. | Partial fixes; current loader protections need verification | User confirmed redraw and compact results implemented but loading bug persisted then. Current question key includes session/index/subject/character and quiz has rejected/pending load handling, making recheck preferable to assuming original failure still present. | C56, C65 | B49
5 | V05 | Verify | 2 | Spotify personal-client connection setup | 0.5–1 day | Verify personal Spotify client-ID onboarding and authentication, then resolve old shared-client report. | Workaround implemented; verify on device | Thread identified shared application authorization restrictions, and users accepted personal-client setup. Current service persists a personal ID and binds tokens to it, with auth tests. No fresh external policy verification performed. | C48
6 | V06 | Verify | 2 | iPad Keyboard Arrow Keys | ½–1 day verification; 1–2 days if Mac focus bug persists | Close confirmed iPad arrow navigation; check Mac iPad-app second lesson batch focus before marking entire report resolved. | iPad confirmed fixed; Mac followup unconfirmed | Current focus effect depends on batch index, active tab and screen focus, which addresses reported lifecycle trigger in principle. Need actual Mac multi-batch verification. | C66
7 | V07 | Verify | 2 | Context cloze replaces the wrong sentence segment | 0.5–1 day verification; 1–2 days if present | Reproduce 思う with 日本の人口について、どう思いますか？ and verify the prefix survives while the correct verb segment is blanked/revealed. Earlier layout and tilde requests were delivered. | Malformed historical cloze; verify current build | The attached reveal screenshot shows 思う、どう思いますか？ while subject details show the full sentence. This identifies a malformed cloze rather than an unexplained details mismatch. | C60
8 | V08 | Verify | 2 | Voices | ½–1 day verification; 1–3 days if native voice selection remains desired | Check current Azure voices/fallback behavior; split native Siri selection into C57 if still wanted. | Historical provider fallback changed; quality not verified | May report describes old all-native fallback. Current Azure service supports named cloud voices, rotating keys and native fallback; latest comment only suggests Bunpro voice quality, not proof current service still broken. | C51
9 | V09 | Verify | 1 | Critical items big widget | 0.25–0.5 day | Check the installed wide widget with Critical mode; close if the existing medium layout meets the request, otherwise clarify desired multi-item layout. | Likely implemented; exact wide-widget expectation uncertain | Code already selects Critical labels in medium widgets and includes count plus top critical item. Request does not specify whether it expects several characters at once. | C06
10 | V10 | Verify | 1 | Transfering subjects from one list to another | 0.25–0.5 day | Verify current copy/move transfer and list filtering satisfy baseline, then close; retain C12 subset/bulk UI separately. | Baseline implemented; later same reporter acknowledges delivery in C12 | Transfer modal supports copy and move; C12 explicitly thanks the already-incorporated feature. C12 is an extension, not a duplicate requiring the original feature twice. | C20
11 | V11 | Verify | 1 | Subject lists quick Review button | 0.5–1 hour | Close implemented quick-review request; verify remembered filter behavior covers follow-up before closing that follow-up. | Quick review delivered; verify remembered filters | List shortcut exists and custom-review configuration persists. Per-list memory versus global memory was not specified, so do not invent a per-list feature. | C26
12 | V12 | Verify | 1 | Ascending order and lowest level first working together | ¼–½ day verification | Verify lowest-level-first + interleave configuration, then close if matching requested ordering. | Implemented; no requester confirmation | Developer says setting added. Current lesson ordering explicitly preserves level groups during interleaving. | C47
13 | V13 | Verify | 1 | Keeping Item Type Order sorting while on Most Overdue First review | ¼–½ day verification | Verify type ordering with Most Overdue First, then close if satisfied. | Implemented in current comparator | Current comparator applies enabled item type order before review-order comparator (critical-item priority can still override by design). This matches radicals first then overdue within type. | C54
14 | V14 | Verify | 2 | A couple of requests | ½–1 day verification | Verify crossword/random-test history avoidance and keyboard preferences; close fulfilled slices, retaining any current reproduction. | Implemented in code; keyboard confirmed | Crossword penalty and random-test recent history both now exist. User confirmed crossword keyboard change in August; initial iPad keyboard report overlaps C44 but this thread bundles distinct repeat avoidance. | C50
15 | V15 | Clarify |  | Japanese translation | 15–30 min triage; implementation unestimated | Obtain one concrete screen/example and desired Japanese/furigana/audio output before scheduling. | Needs scope clarification; developer question unanswered | The request does not identify what should be translated or where audio/furigana belongs. Do not assume it duplicates Japanese-to-Japanese #80. | C11
16 | V16 | Close |  | Lesson search button | No implementation; close the resolved report | Close as delivered, retaining its source history. | Reporter-confirmed delivered | The lesson search button was merged and the reporter says Thank you, that is great. | C07
17 | V17 | Archive |  | Kakehashi - now on web :) | No engineering work | Remove from actionable backlog; retain as community announcement. | Announcement, not a bug or feature request | Developer announces existing web beta; comments are congratulations only. | C10
18 | V18 | Close |  | Level limitation in Vocab reading | No implementation; close resolved report | Close as fixed; keep a regression example for above-level subjects explicitly selected in a list. | Developer and reporter confirm delivered | Developer removed the level limitation and reporter confirmed noticing the fix. | C13
19 | V19 | Close |  | Bookmark indicator and lesson frequency filter | No work for completed baseline; route kana-frequency follow-up to existing frequency request | Close delivered baseline. The later kana-versus-kanji frequency request is retained with C28. | Reporter-confirmed delivered; separate frequency follow-up | Developer says Done and reporter confirms immediately noticing the filled bookmark indicator. Last comment explicitly references another ticket about kana frequency; do not reopen baseline as a broad feature bundle. | C22 | B43
20 | V20 | Close | 1 | How to adjust input font size? | 15–30 min | Close as implemented; point to Review input text size setting. | Implemented; developer confirmation and current setting. | The requested independent review-input font scaling already exists. | C23
21 | V21 | Close | 1 | Crossword suggestion | 15–30 min | Close implemented crossword result display/audio request after routine release check. | Implemented and reporter confirmed; subsequent kana-audio defect also addressed. | Author calls it perfect/working; developer later confirms fix for kana-only audio. | C36
22 | V22 | Close | 1 | Apprentice/Guru item count lesson block | 15–30 min | Close as implemented. | Author confirms feature added. | Requested apprentice/guru lesson thresholds exist and are acknowledged. | C42
23 | V23 | Archive |  | Context sentences audio not working | No implementation; optional current service smoke check | Archive historical developer service-status announcement; retain current voice requests as C51/C57. | Historical announcement superseded by fallback/provider work | Developer announced replacement fallback and users confirmed availability. Current Azure speech implementation has native fallback; this is not an independently actionable open bug without fresh evidence. | C63

## Sources
Original reports and source links
All 80 reports preserved. Work IDs map reports to actions. Evidence is in the notes attached to original titles. One report may contain several outcomes.
|  | Community reports | 67 | All reports | 80
|  | GitHub issues | 13 | Comments read | 249
Report ref | Origin | Original title | Created | Source status | Likes | Comments | Work IDs | Scope / mapping note | Original report link
C01 | Community | Poor handling offline | 2026-09-08 18:12 | open | 1 | 1 | B03 |  | https://kakehashiapp.com/community/b7c2f4f2-cd1a-4cfd-b16b-c6a3100b26d0
C02 | Community | Combine iOS Notifications | 2026-09-05 15:04 | open | 2 | 1 | B29 |  | https://kakehashiapp.com/community/75239481-139c-46fb-b9e8-7df354be04e9
C03 | Community | Multiple Choice | 2026-09-03 11:08 | open | 1 | 10 | B10 |  | https://kakehashiapp.com/community/d579dd8d-bf98-4993-96f0-cfd7b9e52693
C04 | Community | Feature Request: Save sentences to a list | 2026-09-02 23:28 | open | 4 | 3 | B34 |  | https://kakehashiapp.com/community/dfe23011-d902-4615-a496-a3fec02a8d04
C05 | Community | Audio-only vocab reviews | 2026-09-02 21:58 | open | 3 | 6 | B36 |  | https://kakehashiapp.com/community/32f5e9e3-dd2e-4e9a-85d5-d66e6aaac00b
C06 | Community | Critical items big widget | 2026-09-01 13:34 | open | 2 | 0 | V09 |  | https://kakehashiapp.com/community/48d02c3d-330d-4821-a5d6-0a5f40af3cac
C07 | Community | Lesson search button | 2026-08-31 16:08 | open | 1 | 1 | V16 |  | https://kakehashiapp.com/community/35acc028-d118-49bc-9e7e-bdaa245e53b7
C08 | Community | Independent notes | 2026-08-31 10:00 | open | 0 | 0 | B35 |  | https://kakehashiapp.com/community/812ac88d-a237-4788-b991-8d73fac79982
C09 | Community | Links in notes field | 2026-08-31 09:39 | open | 1 | 10 | B11 |  | https://kakehashiapp.com/community/712cdf99-45a1-445c-9acf-7f49f5e2b04b
C10 | Community | Kakehashi - now on web :) | 2026-08-28 18:45 | open | 10 | 2 | V17 |  | https://kakehashiapp.com/community/9a2e1c97-a057-4282-9862-a97588e2a4d2
C11 | Community | Japanese translation | 2026-08-24 20:48 | open | 1 | 1 | V15 |  | https://kakehashiapp.com/community/faaa8291-c807-49b8-8054-10ea3b68f6c0
C12 | Community | Transfer lists and subjects | 2026-08-24 08:41 | open | 0 | 0 | B26 |  | https://kakehashiapp.com/community/62cd19ad-7652-46e5-b3fd-da5ac20e3d2c
C13 | Community | Level limitation in Vocab reading | 2026-08-21 12:00 | open | 1 | 2 | V18 |  | https://kakehashiapp.com/community/f7ef9774-a871-4846-906a-e4428ac505d0
C14 | Community | Basic rich formatting in notes | 2026-08-21 10:09 | open | 1 | 8 | B11, B12 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/fe972916-2df7-4c98-937a-bb6b43ffcbe5
C15 | Community | Vocabulary Kanji Composition | 2026-08-19 16:37 | open | 1 | 0 | B41 |  | https://kakehashiapp.com/community/57cf97a3-a8b2-4d7c-8caa-0cff4024581e
C16 | Community | Reading note cut off in unified learning (iPhone Air) | 2026-08-15 10:13 | open | 1 | 4 | B15 |  | https://kakehashiapp.com/community/b4b957aa-658d-4ce8-9bda-a832dbf3b0b1
C17 | Community | Temporarily mute audio | 2026-08-12 16:11 | open | 1 | 1 | B37 |  | https://kakehashiapp.com/community/fa2f1b96-b917-4d11-8861-f0404c7279c2
C18 | Community | Music lyrics not working? | 2026-08-12 14:14 | open | 3 | 3 | B19 |  | https://kakehashiapp.com/community/e06878ea-6f1d-45d8-9fd5-1fd86244a420
C19 | Community | review forecast duplicate | 2026-08-12 01:56 | open | 0 | 0 | B18 |  | https://kakehashiapp.com/community/634745d3-e07c-43db-8e31-34642b57f43f
C20 | Community | Transfering subjects from one list to another | 2026-08-11 16:37 | open | 0 | 1 | V10 |  | https://kakehashiapp.com/community/70dce87d-5d52-4766-b644-19565e2091ad
C21 | Community | Review word obstruction | 2026-08-11 09:29 | open | 0 | 2 | B13 |  | https://kakehashiapp.com/community/026bbef7-741a-471e-9376-0eb8ac70b1e4
C22 | Community | Previously Bookmarked Indicator | 2026-08-08 03:29 | open | 1 | 3 | B43, V19 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/c7a9711c-5687-4039-8e1a-9d1eb0b6b1c8
C23 | Community | How to adjust input font size? | 2026-08-04 22:19 | open | 1 | 1 | V20 |  | https://kakehashiapp.com/community/bf664984-5ab6-4d3b-acb7-d35c007f57c7
C24 | Community | Review Count Displaying Incorrectly | 2026-07-28 00:34 | open | 1 | 1 | B09 |  | https://kakehashiapp.com/community/aa7db109-6306-450c-a7c0-0208c8f37ed2
C25 | Community | Additional level stats | 2026-07-26 18:12 | open | 1 | 4 | B44 |  | https://kakehashiapp.com/community/c7fc2b2a-ec35-42df-b28b-640ca9eaccf3
C26 | Community | Subject lists quick Review button | 2026-07-25 20:32 | open | 1 | 2 | V11 |  | https://kakehashiapp.com/community/45cadbca-ee19-49fc-85bf-ad1e4e2dcbba
C27 | Community | Feature request for newbies | 2026-07-23 15:43 | open | 1 | 7 | B26, B42 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/c5eb44ba-aa53-43aa-9c51-e4d91c19971e
C28 | Community | Custom Review List (Sorted by JLPT) | 2026-07-16 02:23 | open | 3 | 10 | B43 |  | https://kakehashiapp.com/community/191d89d6-da16-4c8a-817e-026f2e4e274c
C29 | Community | Undo last answer | 2026-07-15 16:49 | open | 10 | 7 | B24 |  | https://kakehashiapp.com/community/c27d54e3-c0c6-485f-b651-30baed69fd10
C30 | Community | Offline mode not working | 2026-07-14 22:37 | open | 1 | 2 | B04 |  | https://kakehashiapp.com/community/b826b522-30ff-4ffb-8c89-18c3c7ec5d78
C31 | Community | Anime Title Formatting | 2026-07-14 18:17 | open | 0 | 0 | B40 |  | https://kakehashiapp.com/community/e90a7b74-d924-4f1c-909c-5bdb5644ac41
C32 | Community | question | 2026-07-14 08:08 | open | 0 | 2 | B33 |  | https://kakehashiapp.com/community/f7479d44-1c15-4a3d-977e-516b37edfc45
C33 | Community | Reading note/Meaning note disappearing | 2026-07-10 14:26 | open | 0 | 4 | B01 |  | https://kakehashiapp.com/community/c57e9511-f409-40e9-9281-6ed698512267
C34 | Community | Interleave lessons and reviews (suggestion) | 2026-06-30 02:00 | open | 0 | 0 | B47 |  | https://kakehashiapp.com/community/8d5fc0bc-cee1-4942-9352-9a29a40a0218
C35 | Community | Text box not registering keystrokes on reviews | 2026-06-29 09:37 | open | 0 | 0 | V02 |  | https://kakehashiapp.com/community/8d6a11bc-235a-4a81-b5f3-9271ce55c41f
C36 | Community | Crossword suggestion | 2026-06-29 07:53 | open | 1 | 5 | V21 |  | https://kakehashiapp.com/community/5c4caeba-8084-4209-9a32-4c11a7b6e733
C37 | Community | Vocab reviews not centered; level & SRS not visible | 2026-06-29 07:29 | open | 0 | 2 | B14 |  | https://kakehashiapp.com/community/111a08ca-b8de-46d1-b42f-4b47d156b517
C38 | Community | [Android] Quiz Font Size Issue | 2026-06-24 23:24 | open | 3 | 2 | B06 |  | https://kakehashiapp.com/community/bf6c40ba-b760-4317-9503-e56a0f325b37
C39 | Community | Occasionally Kanji are tiny | 2026-06-21 05:40 | open | 3 | 2 | B06 |  | https://kakehashiapp.com/community/6b9027ee-7dbe-4455-ae7b-dd0972d966df
C40 | Community | 200% | 2026-06-20 04:07 | open | 2 | 9 | B16, B33 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/bbabd0a0-b6e4-4ab2-9fb6-6c221b01341e
C41 | Community | Screen spazzing out when i try to add a note | 2026-06-18 22:53 | open | 1 | 2 | V03 |  | https://kakehashiapp.com/community/9980ff84-0802-4de8-aadb-04ea68269cc2
C42 | Community | Apprentice/Guru item count lesson block | 2026-06-17 18:41 | open | 1 | 2 | V22 |  | https://kakehashiapp.com/community/7a9653a7-50d9-4f96-b191-d0a7bd8edd8f
C43 | Community | Adding a cbz/cbr manga reader | 2026-06-14 20:31 | open | 3 | 1 | B51 |  | https://kakehashiapp.com/community/b8f98809-d8bd-4265-afa5-162a5be0816f
C44 | Community | switch keyboard automatically | 2026-06-13 14:58 | open | 4 | 4 | B02 |  | https://kakehashiapp.com/community/192c3228-19c2-4688-9941-466ce698f72a
C45 | Community | Stroke order visualization | 2026-06-12 15:17 | open | 3 | 2 | B30 |  | https://kakehashiapp.com/community/8b13cf8b-a2e0-4806-ab66-116d60067a4d
C46 | Community | Cut off text; lesson count; copy paste | 2026-06-10 01:46 | open | 1 | 1 | B15, B31 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/1b1755b7-9db4-40fa-b1ac-f403ec5bd3a7
C47 | Community | Ascending order and lowest level first working together | 2026-06-09 05:05 | open | 1 | 1 | V12 |  | https://kakehashiapp.com/community/e07e5d09-8da6-4ecf-b7fb-d05dcd31fbcb
C48 | Community | Spotify | 2026-06-06 11:14 | open | 8 | 10 | V05 |  | https://kakehashiapp.com/community/09131848-6c3a-442e-a4f5-23c089b37c14
C49 | Community | Custom subject list filter | 2026-06-04 18:10 | open | 1 | 10 | B27 |  | https://kakehashiapp.com/community/fb0cb5db-e54f-43b1-b787-97719175801a
C50 | Community | A couple of requests | 2026-06-01 00:09 | open | 2 | 5 | V14 |  | https://kakehashiapp.com/community/ab3c1abc-7514-4c1a-aa2e-52167b44a813
C51 | Community | Voices | 2026-05-22 23:20 | open | 2 | 4 | V08 |  | https://kakehashiapp.com/community/15e1d664-8e33-4906-80da-4a04ce9be431
C52 | Community | [Android] Daily Lesson Reminder issues | 2026-05-21 17:42 | open | 2 | 1 | B17 |  | https://kakehashiapp.com/community/02dcd652-5079-4681-ad43-9a013cbeb0b0
C53 | Community | Lesson/Review count | 2026-05-21 13:27 | open | 3 | 6 | B09 |  | https://kakehashiapp.com/community/31e14002-b92a-4d81-91b1-2fba0adc5877
C54 | Community | Keeping Item Type Order sorting while on Most Overdue First review | 2026-05-19 16:06 | open | 1 | 1 | V13 |  | https://kakehashiapp.com/community/1602049e-745f-4bdb-a146-a5b3019c0b6b
C55 | Community | [Android] Vocabulary lessons take too long to load | 2026-05-18 15:20 | open | 4 | 5 | B05 |  | https://kakehashiapp.com/community/ab3bf99e-4094-418e-8bbe-021231ee5b3e
C56 | Community | Lock screen widget/apple watch complication? | 2026-05-17 19:04 | open | 2 | 5 | B49, V04 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/d00e65c3-7c9c-4b86-8386-fe7e376f9e28
C57 | Community | Context Sentence TTS Voice | 2026-05-13 11:15 | open | 1 | 4 | B48 |  | https://kakehashiapp.com/community/b05f5e5b-a0cd-476f-955f-dbbbb73320fa
C58 | Community | Minor issue with text cropping | 2026-05-11 04:02 | open | 1 | 2 | B15 |  | https://kakehashiapp.com/community/9f6db376-cab8-4f7e-b417-3f02aba651cc
C59 | Community | Recent Unlocks Suggestion | 2026-05-10 15:12 | open | 1 | 2 | B28 |  | https://kakehashiapp.com/community/9817dcf1-f971-4bb9-b0bf-80b685abafdb
C60 | Community | Context Sentences Extra Study suggestions | 2026-05-08 01:51 | open | 1 | 14 | V07 |  | https://kakehashiapp.com/community/ee5cfd98-1a2d-4d9a-9faf-948038f91386
C61 | Community | Small reset bug | 2026-05-03 10:49 | open | 1 | 2 | B32 |  | https://kakehashiapp.com/community/2457b748-6331-4807-abee-147a65d076eb
C62 | Community | Android glitches | 2026-05-03 09:13 | open | 4 | 5 | B06, B07, B21 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/7e3260de-3d3e-4d6f-8eff-0b540bf2f0a2
C63 | Community | Context sentences audio not working | 2026-05-01 20:20 | open | 3 | 3 | V23 |  | https://kakehashiapp.com/community/62f18945-7bb8-4ce7-9674-6cec0c15c4ce
C64 | Community | AirPlay and screen share don’t work | 2026-04-25 22:23 | open | 2 | 8 | B20 |  | https://kakehashiapp.com/community/63e1ac95-6bc9-42f6-ac10-d81743ca4d1f
C65 | Community | kanji writing, some kanji stuck loading | 2026-04-16 19:09 | open | 1 | 3 | V04 |  | https://kakehashiapp.com/community/22a4f4a8-f3b9-4eb4-bce1-f29941ed9655
C66 | Community | iPad Keyboard Arrow Keys | 2026-04-13 04:16 | open | 2 | 5 | V06 |  | https://kakehashiapp.com/community/d6ad6aba-e797-4403-941c-595c82db4300
C67 | Community | Apple Watch Review | 2026-03-08 07:13 | open | 8 | 4 | B49, B50 | One report spans several work items; see each remaining action. | https://kakehashiapp.com/community/a1687fed-7bfd-4c27-a185-cd13ba195a7f
G80 | GitHub | [Feature]: As much Japanese to Japanese options as possible (with examples) | 2026-09-08 20:53 | open |  | 0 | B46 |  | https://github.com/Portego-00/Kakehashi/issues/80
G77 | GitHub | [Bug]: When using the extra fonts the default font shows for a split second | 2026-09-08 19:17 | open |  | 0 | B38 |  | https://github.com/Portego-00/Kakehashi/issues/77
G76 | GitHub | [Bug]: Superfluous Submit Answer button in multiple choice extra reviews | 2026-09-08 19:05 | open |  | 0 | B22 |  | https://github.com/Portego-00/Kakehashi/issues/76
G75 | GitHub | [Feature]: Add automatic audio when answer is correct in Context Sentences reviews | 2026-09-08 18:59 | open |  | 0 | B23 |  | https://github.com/Portego-00/Kakehashi/issues/75
G72 | GitHub | [Bug]: In reviews and Audio quiz the multiple choice menu disappears sometimes | 2026-09-08 17:29 | open |  | 0 | B08 |  | https://github.com/Portego-00/Kakehashi/issues/72
G71 | GitHub | [Feature]: Customised context sentences improvements | 2026-09-08 17:25 | open |  | 1 | B45 |  | https://github.com/Portego-00/Kakehashi/issues/71
G70 | GitHub | [Bug]: When resuming picked lessons, random lessons are added on | 2026-09-08 16:54 | open |  | 2 | V01 |  | https://github.com/Portego-00/Kakehashi/issues/70
G68 | GitHub | [Bug]: Editing screen and rich formatting | 2026-09-08 15:47 | open |  | 0 | B12 |  | https://github.com/Portego-00/Kakehashi/issues/68
G66 | GitHub | [Feature]: Integral notebook | 2026-09-06 10:52 | open |  | 5 | B35 |  | https://github.com/Portego-00/Kakehashi/issues/66
G65 | GitHub | [Bug]: Links in notes | 2026-09-06 10:02 | open |  | 7 | B11 |  | https://github.com/Portego-00/Kakehashi/issues/65
G58 | GitHub | [Feature]: Export Media Context Sentences to Anki (willing to implement myself) | 2026-08-24 01:49 | open |  | 1 | B25 |  | https://github.com/Portego-00/Kakehashi/issues/58
G54 | GitHub | [Bug]: Review text is sometimes broken on Android | 2026-07-28 01:06 | open |  | 1 | B07 |  | https://github.com/Portego-00/Kakehashi/issues/54
G50 | GitHub | [Bug]: level recap layout broken | 2026-07-07 04:21 | open |  | 1 | B39 |  | https://github.com/Portego-00/Kakehashi/issues/50